## GANTT
Interreg VI-A Romania-Hungary Indicative Calendar for Programme Implementation*
|  | 2023 | [6 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030
|  | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
Open Call 1 - 70% allocation 42,8 MEur | Launching | bar: 2023 June to 2023 Aug
Submission | bar: 2023 Sept to 2024 Feb
Assesment | bar: 2023 Dec to 2024 Aug
Selection | bar: 2023 Dec to 2024 Aug
Contracting | bar: 2024 June to 2024 Nov
Implementation | bar: 2024 Sept to 2026 Nov
Reimbursement | bar: 2024 Sept; 2024 Dec; 2025 Mar; 2025 June; 2025 Sept to 2025 Dec; 2026 Mar; 2026 June; 2026 Sept; 2026 Dec to 2027 Feb
Open Call 2 - 30% allocation 18,3 MEur | Launching | bar: 2024 June to 2024 Aug
Submission | bar: 2024 Sept to 2025 Feb
Assesment | bar: 2025 Mar to 2025 Aug
Selection | bar: 2025 Mar to 2025 Aug
Contracting | bar: 2025 June to 2025 Nov
Implementation | bar: 2025 Sept to 2027 Nov
Reimbursement | bar: 2025 Sept; 2025 Dec; 2026 Mar; 2026 June; 2026 Sept to 2026 Dec; 2027 Mar; 2027 June; 2027 Sept; 2027 Dec to 2028 Feb
Restricted Call - OSIs 70,3 MEur | Launching | bar: 2023 July to 2023 Sept
Submission | bar: 2023 Oct to 2024 Mar
Assesment | bar: 2024 Apr to 2024 Sept
Selection | bar: 2024 Apr to 2024 Sept
Contracting | bar: 2024 July to 2024 Dec
Implementation | bar: 2025 Jan to 2027 Dec
Reimbursement | bar: 2025 Jan; 2025 Apr; 2025 July; 2025 Oct; 2026 Jan; 2026 Apr; 2026 July; 2026 Oct; 2027 Jan; 2027 Apr; 2027 July; 2027 Oct; 2028 Jan to 2028 Mar
Open Call 3 - savings | Launching | bar: 2027 June to 2027 July
Submission | bar: 2027 Aug to 2027 Oct
Assesment | bar: 2027 Nov to 2028 Jan
Selection | bar: 2027 Nov to 2028 Jan
Contracting | bar: 2028 Feb to 2028 Apr
Implementation | bar: 2028 May to 2030 Apr
Reimbursement | bar: 2028 May; 2028 Aug; 2028 Nov; 2029 Feb; 2029 May to 2029 Aug; 2029 Nov; 2030 Feb; 2030 May to 2030 July
P2P and Normal Projects in the same period
P2P projects
Normal Projects
OSIs
P2P and Normal Projects
Normal Projects
* The present Calendar is indicative and it wil be discussed with the MC.